## DataSheet
Id | TrustId | SubmissionId | MetaSubmissionId | Research Ethics Committee Reference Number | Name of Trial | Date of Receipt of Valid Research Application | Date of NHS Permission | First Patient Recruited? | Date of First Patient Recruited | Duration between VRA and NHS Permission | Duration between NHS Permission and First Patient | Duration between VRA and First Patient | Benchmark Met | AddedByUserId | AmendedByUserId | DateAdded | DateAmended | A - Permissions delayed/denied | B - Suspended by sponsor | C - Closed by sponsor | D - Sponsor Delays | E - Staff availability issues | F - No patients seen | G - No patients consented | H - Contracting delays | I - Rare diseases | J - Other | K - Not Used | L - Not Used | M - Not Used | N - Not Used | O - Not Used | Comments | Reasons for delay correspond to: | Errors
70728 | 1067 | 3236 | 36 | 11/WM/0220 | TEAMM:Tackling Early Morbidity and Mortality of Myeloma | 2015-01-05 | 2015-01-19 | Yes | 2015-05-29 | 14 | 130 | 144 | No | Unknown | Unknown | 2016-01-28 | 2016-01-28 |  |  |  | Y |  |  |  |  | Y | [6 empty] | Site initiation visit 15/04/15 | Sponsor
70729 | 1067 | 3236 | 36 | 14/NE/1111 | ADENOMA; Accuracy of Detection using ENdocuff Optimisation of Mucosal Abnormalities. | 2015-01-12 | 2015-01-26 | Yes | 2015-02-10 | 14 | 15 | 29 | Yes | Unknown | Unknown | 2016-01-28 | 42397 | [16 empty] | Please Select...
70730 | 1067 | 3236 | 36 | 14/LO/0721 | SIPS Jnr | 2015-01-23 | 2015-01-29 | Yes | 2015-02-02 | 6 | 4 | 10 | Yes | Unknown | Unknown | 2016-01-28 | 42397 | [16 empty] | Please Select...
70731 | 1067 | 3236 | 36 | 12/WM/0340 | FixDT:UK Fixation of Distal Tibia fractures Trial | 2015-02-05 | 2015-02-17 | Yes | 2015-03-09 | 12 | 20 | 32 | Yes | Unknown | Unknown | 2016-01-28 | 42397 | [16 empty] | Please Select...
70732 | 1067 | 3236 | 36 | 14/LO/1043 | LEAVO:Multicentre ph 3 double masked RCT comparing clinical and cost effectiveness of ranibizumab vs afibercept vs bevacizumab for macular oedema due to cenral vein occulusion | 2015-02-03 | 2015-02-17 | Yes | 2015-05-05 | 14 | 77 | 91 | No | Unknown | Unknown | 2016-01-28 | 42397 |  |  |  | Y | [11 empty] | Green Light not received until 22nd April | Sponsor
70733 | 1067 | 3236 | 36 | 10/HO802/46 | REVIVED:Revascularisation for Ischaemic Ventricular Dysfunction | 2015-03-09 | 2015-03-23 | Yes | 2015-05-11 | 14 | 49 | 63 | Yes | Unknown | Unknown | 2016-01-28 | 42397 | [15 empty] | Delay due to delay in some of the investigations required for screening | NHS Provider
70734 | 1067 | 3236 | 36 | 13/SC/0645 | Pre-Eclampsia in Hospital -Early Induction of Expectant Mothers-PHOENIX | 2015-03-19 | 2015-03-30 | Yes | 2015-09-02 | 11 | 156 | 167 | No | Unknown | Unknown | 2016-01-28 | 42397 | [6 empty] | Y | [8 empty] | No eligible patients seen | Neither
70735 | 1067 | 3236 | 36 | 13/YH/0377 | BIG CACTUS; A study to assess clinical and cost effectiveness of aphasia computer treatment versus usual stimulation or attension | 2015-04-21 | 2015-05-05 | Yes | 2015-05-22 | 14 | 17 | 31 | Yes | Unknown | Unknown | 2016-01-28 | 42397 | [16 empty] | Please Select...
70736 | 1067 | 3236 | 36 | 14/SC/0157 | PARAMEDIC 2; Pre hospital assessment of role of Adrenaline; measuring effectiveness of drug administration on cardiac arrest | 2014-10-24 | 2015-05-21 | Yes - Date Unavailable |  | 209 |  |  |  | Unknown | Unknown | 2016-01-28 | 42397 | Y |  |  | Y | Y | [10 empty] | Single SSI submitted without discussion with Trust. Acrual not going to individual sites | Sponsor
70737 | 1067 | 3236 | 36 | 14/SC/1345 | PRISM;The Effectiveness of Progesterone to prevent miscarriage in women with early pregnancy bleeding. | 2015-05-29 | 2015-06-01 | Yes | 2015-06-18 | 3 | 17 | 20 | Yes | Unknown | Unknown | 2016-01-28 | 42397 | [16 empty] | Please Select...
70738 | 1067 | 3236 | 36 | 11/SS/0100 | FOCUS;Multi centre randomised trial to establish the effects of routine administration of Fluoxetine for 6 months in patients with recent stroke. | 2015-06-08 | 2015-06-10 | Yes | 2015-09-02 | 2 | 84 | 86 | No | Unknown | Unknown | 2016-01-28 | 42397 | [5 empty] | Y | [10 empty] | NHS Provider
70739 | 1067 | 3236 | 36 | 12/NW/0361 | SANAD II;Pragmatic randomisedcontrol trial comparing effectiveness and cost effectiveness of Levetiracetam and Zonisamide versus standard treatments for Epilepsy. | 2015-06-09 | 2015-06-22 | Yes | 2015-10-19 | 13 | 119 | 132 | No | Unknown | Unknown | 2016-01-28 | 42397 |  |  |  | Y |  | Y | [9 empty] | Gren light 12/10/15 | Sponsor
70740 | 1067 | 3236 | 36 | 14/LO/2061 | PIMS;Multicentre comparative randomised control clinical trial comparing face down positioning with an inactive face forward position on the outcome of surgery for large macular holes. | 2015-06-09 | 2015-06-23 | Yes | 2015-08-13 | 14 | 51 | 65 | Yes | Unknown | Unknown | 2016-01-28 | 42397 | [15 empty] | Site awaiting green light. | Sponsor
70741 | 1067 | 3236 | 36 | 13/WM/0419 | MAMM0-50 mammogram surveillance in breast cancer | 2015-07-15 | 2015-07-22 | No |  | 7 |  |  |  | Unknown | Unknown | 2016-01-28 | 42397 | [9 empty] | Y | [5 empty] | problem with machine on site | NHS Provider
72380 | 1067 | 3236 | 36 | 15/WS/0129 | Early intervention to improve motor outcome after perinatal stroke: eTIPS pilot feasibility study | 2015-10-09 | 2015-10-14 | Yes | 2015-11-09 | 5 | 26 | 31 | Yes | Unknown | Unknown | 2016-01-28 | 42397 | [16 empty] | Please Select...
72381 | 1067 | 3236 | 36 | 13/NE/0339 | Glycerine Trinitrate for Retained Placenta (GOT-IT Trial) | 2015-09-30 | 2015-10-05 | Yes | 2015-12-10 | 5 | 66 | 71 | No | Unknown | Unknown | 2016-01-28 | 42397 | [6 empty] | Y | [8 empty] | no eligible patients seen | NHS Provider
72382 | 1067 | 3236 | 36 | 14/SW/0019 | Restrictive versus Liberal Fluid THerapy in Major Abdominal Surgery | 2015-10-15 | 2015-10-21 | Yes | 2015-11-20 | 6 | 30 | 36 | Yes | Unknown | Unknown | 2016-01-28 | 42397 | [16 empty] | Please Select...
72383 | 1067 | 3236 | 36 | 14/SC/0237 | A randomised controlled trial to determine the clinical and cost effectiveness of invasive urodynamic studies for diagnosis and management of bladder outlet obstruction in men in the National Health Service (NHS) | 2015-10-05 | 2015-10-14 | Yes | 2015-11-18 | 9 | 35 | 44 | Yes | Unknown | Unknown | 2016-01-28 | 42397 | [16 empty] | Please Select...
72384 | 1067 | 3236 | 36 | 11/LO/0927 | Warwick Hip Trauma Evaluation: A Comprehensive Cohort Study of Patients with Fracture of the Proximal Femur. The WHiTE Study | 2015-11-02 | 2015-11-10 | Yes | 2015-12-16 | 8 | 36 | 44 | Yes | Unknown | Unknown | 2016-01-28 | 42397 | [16 empty] | Please Select...
72385 | 1067 | 3236 | 36 | 14/WM/1098 | Cemented Thompsons vs Modern polished tapered stem. A randomised controlled trial comparing the Thompsons versus the Exeter? polished taper stem and Unitrax? head in the treatment of displaced intracapsular fractures of the proximal femur ? The WHiTE: HEMI Study. | 2015-11-02 | 2015-11-11 | Yes | 2015-12-18 | 9 | 37 | 46 | Yes | Unknown | Unknown | 2016-01-28 | 42397 | [16 empty] | Please Select...
72386 | 1067 | 3236 | 36 | 15/NE/0255 | Let's Talk About Sleep! A new approach for improving infant sleep-sharing safety: a feasibility study | 2015-10-21 | 2015-11-04 | Yes | 2015-11-18 | 14 | 14 | 28 | Yes | Unknown | Unknown | 2016-01-28 | 42397 | [16 empty] | Please Select...
72387 | 1067 | 3236 | 36 | 13/WS/0056 | Cancer and Venous Access (CAVA) - A randomised controlled trial with associated qualitative research of venous access devices for the delivery of long-term chemotherapy | 2015-11-26 | 2015-12-03 | Yes | 2016-01-04 | 7 | 32 | 39 | Yes | Unknown | Unknown | 2016-01-28 | 42397 | [16 empty] | Please Select...
72388 | 1067 | 3236 | 36 | 14/NI/0002 | AN OPEN LABEL, REGISTRY STUDY OF THE SAFETY OF ILUVIEN? 190 MICROGRAMS INTRAVITREAL IMPLANT IN APPLICATOR | 2015-12-07 | 2015-12-10 | Yes | 2015-12-10 | 3 | 0 | 3 | Yes | Unknown | Unknown | 2016-01-28 | 42397 | [16 empty] | Please Select...
Upload Submission
Validate

## Hidden Data (hidden)
SpreadsheetOne - Hidden Data
******** PLEASE DO NOT CHANGE ANY OF THESE VALUES ********
| Hidden Data Key | Hidden Data Value |  | XML |  | Class
| Is First Open | FALSE |  | <?xml version="1.0" encoding="utf-16"?> <DataTableDataExportContainerOfPerformanceInitiationDetail xmlns:xsd="http://www.w3.org/2001/XMLSchema" xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance"> <DataTypeName>Exbos.Applications.NHSRBVP.Components.BusinessObjects.PerformanceInitiationDetail, Exbos.Applications.NHSRBVP.Components.BusinessObjects, Version=1.0.10.0, Culture=neutral, PublicKeyToken=null</DataTypeName> <Site Id="1" AddressId="-1" StatusId="51" TypeId="401" CultureId="1" AddedByUserId="1" AmendedByUserId="1" DateAdded="2013-06-15T22:56:16" DateAmended="2013-06-15T22:56:16"> <Name>CTP Submission Platform</Name> <Description/> </Site> </DataTableDataExportContainerOfPerformanceInitiationDetail> |  | PerformanceInitiationDetail
| Development Mode | FALSE
| Data Id | 3236
| User Id | -1
| Data Id | 40
<ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>true</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>1</Order> <Name>Id</Name> <FriendlyName>Id</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>-1</DataTypeId> <DataType>None</DataType> <MaxLength>-1</MaxLength> <DataTypeCache/> <IncludePleaseSelect>true</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>true</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">-1</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>false</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>2</Order> <Name>TrustId</Name> <FriendlyName>TrustId</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>-1</DataTypeId> <DataType>None</DataType> <MaxLength>-1</MaxLength> <DataTypeCache/> <IncludePleaseSelect>true</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">1067</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>false</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>3</Order> <Name>SubmissionId</Name> <FriendlyName>SubmissionId</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>-1</DataTypeId> <DataType>None</DataType> <MaxLength>-1</MaxLength> <DataTypeCache/> <IncludePleaseSelect>true</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">3236</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>false</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>4</Order> <Name>MetaSubmissionId</Name> <FriendlyName>MetaSubmissionId</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>-1</DataTypeId> <DataType>None</DataType> <MaxLength>-1</MaxLength> <DataTypeCache/> <IncludePleaseSelect>true</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">36</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>String</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>NotEmpty</ErrorValidationRule> <Visible>true</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>5</Order> <Name>ReferenceNumber</Name> <FriendlyName>Research Ethics Committee Reference Number</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>-1</DataTypeId> <DataType>None</DataType> <MaxLength>-1</MaxLength> <DataTypeCache/> <IncludePleaseSelect>true</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:string"/> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>String</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>NotEmpty</ErrorValidationRule> <Visible>true</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>6</Order> <Name>TrialName</Name> <FriendlyName>Name of Trial</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>-1</DataTypeId> <DataType>None</DataType> <MaxLength>-1</MaxLength> <DataTypeCache/> <IncludePleaseSelect>true</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:string"/> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>DateTime</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>Date</ErrorValidationRule> <Visible>true</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>7</Order> <Name>ReceiptDate</Name> <FriendlyName>Date of Receipt of Valid Research Application</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>-1</DataTypeId> <DataType>None</DataType> <MaxLength>-1</MaxLength> <DataTypeCache/> <IncludePleaseSelect>true</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:dateTime">1753-01-01T12:00:00</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>true</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>DateTime</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>Date</ErrorValidationRule> <Visible>true</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>8</Order> <Name>PermissionDate</Name> <FriendlyName>Date of NHS Permission</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>-1</DataTypeId> <DataType>None</DataType> <MaxLength>-1</MaxLength> <DataTypeCache/> <IncludePleaseSelect>true</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:dateTime">1753-01-01T12:00:00</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>true</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>9</Order> <Name>FirstPatientRecruitedTypeId</Name> <FriendlyName>First Patient Recruited?</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>1400</DataTypeId> <DataType>Type</DataType> <MaxLength>-1</MaxLength> <DataTypeCache> <item> <key> <int>1401</int> </key> <value> <string>Yes</string> </value> </item> <item> <key> <int>1402</int> </key> <value> <string>Yes - Date Unavailable</string> </value> </item> <item> <key> <int>1403</int> </key> <value> <string>No</string> </value> </item> </DataTypeCache> <IncludePleaseSelect>true</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">-1</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>DateTime</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>Date</ErrorValidationRule> <Visible>true</Visible> <CanBeEmpty>true</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>10</Order> <Name>FirstPatientRecruitedDate</Name> <FriendlyName>Date of First Patient Recruited</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>-1</DataTypeId> <DataType>None</DataType> <MaxLength>-1</MaxLength> <DataTypeCache/> <IncludePleaseSelect>true</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:dateTime">1753-01-01T12:00:00</DefaultValue> <UseCustomErrorValidator>true</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>Integer</ErrorValidationRule> <Visible>true</Visible> <CanBeEmpty>true</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>11</Order> <Name>ApplicationToPermissionDuration</Name> <FriendlyName>Duration between VRA and NHS Permission</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>-1</DataTypeId> <DataType>None</DataType> <MaxLength>-1</MaxLength> <DataTypeCache/> <IncludePleaseSelect>true</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>true</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">-99999911</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>true</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>Integer</ErrorValidationRule> <Visible>true</Visible> <CanBeEmpty>true</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>12</Order> <Name>PermissionToFirstPatientDuration</Name> <FriendlyName>Duration between NHS Permission and First Patient</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>-1</DataTypeId> <DataType>None</DataType> <MaxLength>-1</MaxLength> <DataTypeCache/> <IncludePleaseSelect>true</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>true</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">-99999911</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>true</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>Integer</ErrorValidationRule> <Visible>true</Visible> <CanBeEmpty>true</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>13</Order> <Name>ApplicationToFirstPatientDuration</Name> <FriendlyName>Duration between VRA and First Patient</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>-1</DataTypeId> <DataType>None</DataType> <MaxLength>-1</MaxLength> <DataTypeCache/> <IncludePleaseSelect>true</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>true</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">-99999911</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>true</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>true</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>14</Order> <Name>BenchmarkMetTypeId</Name> <FriendlyName>Benchmark Met</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>1500</DataTypeId> <DataType>Type</DataType> <MaxLength>-1</MaxLength> <DataTypeCache> <item> <key> <int>1501</int> </key> <value> <string>Yes</string> </value> </item> <item> <key> <int>1502</int> </key> <value> <string>No</string> </value> </item> <item> <key> <int>1503</int> </key> <value> <string>Within 70 Days</string> </value> </item> <item> <key> <int>-1</int> </key> <value> <string>Please Select...</string> </value> </item> </DataTypeCache> <IncludePleaseSelect>true</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>true</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">-1</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>true</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>false</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>15</Order> <Name>AddedByUserId</Name> <FriendlyName>AddedByUserId</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>-1</DataTypeId> <DataType>Site</DataType> <MaxLength>-1</MaxLength> <DataTypeCache> <item> <key> <int>294</int> </key> <value> <string>Unknown</string> </value> </item> </DataTypeCache> <IncludePleaseSelect>true</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">-1</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>false</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>16</Order> <Name>AmendedByUserId</Name> <FriendlyName>AmendedByUserId</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>-1</DataTypeId> <DataType>Site</DataType> <MaxLength>-1</MaxLength> <DataTypeCache> <item> <key> <int>294</int> </key> <value> <string>Unknown</string> </value> </item> </DataTypeCache> <IncludePleaseSelect>true</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">-1</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>DateTime</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>false</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>17</Order> <Name>DateAdded</Name> <FriendlyName>DateAdded</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>-1</DataTypeId> <DataType>None</DataType> <MaxLength>-1</MaxLength> <DataTypeCache/> <IncludePleaseSelect>true</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:dateTime">2016-01-28T15:04:59.842625+00:00</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>DateTime</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>false</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>18</Order> <Name>DateAmended</Name> <FriendlyName>DateAmended</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>-1</DataTypeId> <DataType>None</DataType> <MaxLength>-1</MaxLength> <DataTypeCache/> <IncludePleaseSelect>true</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:dateTime">2016-01-28T15:04:59.842625+00:00</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>true</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>19</Order> <Name>NotMetATypeId</Name> <FriendlyName>A - Permissions delayed/denied</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>2200</DataTypeId> <DataType>Type</DataType> <MaxLength>-1</MaxLength> <DataTypeCache> <item> <key> <int>2201</int> </key> <value> <string>Y</string> </value> </item> <item> <key> <int>2202</int> </key> <value> <string> </string> </value> </item> </DataTypeCache> <IncludePleaseSelect>false</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">2202</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>true</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>20</Order> <Name>NotMetBTypeId</Name> <FriendlyName>B - Suspended by sponsor</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>2200</DataTypeId> <DataType>Type</DataType> <MaxLength>-1</MaxLength> <DataTypeCache> <item> <key> <int>2201</int> </key> <value> <string>Y</string> </value> </item> <item> <key> <int>2202</int> </key> <value> <string> </string> </value> </item> </DataTypeCache> <IncludePleaseSelect>false</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">2202</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>true</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>21</Order> <Name>NotMetCTypeId</Name> <FriendlyName>C - Closed by sponsor</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>2200</DataTypeId> <DataType>Type</DataType> <MaxLength>-1</MaxLength> <DataTypeCache> <item> <key> <int>2201</int> </key> <value> <string>Y</string> </value> </item> <item> <key> <int>2202</int> </key> <value> <string> </string> </value> </item> </DataTypeCache> <IncludePleaseSelect>false</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">2202</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>true</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>22</Order> <Name>NotMetDTypeId</Name> <FriendlyName>D - Sponsor Delays</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>2200</DataTypeId> <DataType>Type</DataType> <MaxLength>-1</MaxLength> <DataTypeCache> <item> <key> <int>2201</int> </key> <value> <string>Y</string> </value> </item> <item> <key> <int>2202</int> </key> <value> <string> </string> </value> </item> </DataTypeCache> <IncludePleaseSelect>false</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">2202</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>true</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>23</Order> <Name>NotMetETypeId</Name> <FriendlyName>E - Staff availability issues</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>2200</DataTypeId> <DataType>Type</DataType> <MaxLength>-1</MaxLength> <DataTypeCache> <item> <key> <int>2201</int> </key> <value> <string>Y</string> </value> </item> <item> <key> <int>2202</int> </key> <value> <string> </string> </value> </item> </DataTypeCache> <IncludePleaseSelect>false</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">2202</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>true</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>24</Order> <Name>NotMetFTypeId</Name> <FriendlyName>F - No patients seen</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>2200</DataTypeId> <DataType>Type</DataType> <MaxLength>-1</MaxLength> <DataTypeCache> <item> <key> <int>2201</int> </key> <value> <string>Y</string> </value> </item> <item> <key> <int>2202</int> </key> <value> <string> </string> </value> </item> </DataTypeCache> <IncludePleaseSelect>false</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">2202</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>true</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>25</Order> <Name>NotMetGTypeId</Name> <FriendlyName>G - No patients consented</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>2200</DataTypeId> <DataType>Type</DataType> <MaxLength>-1</MaxLength> <DataTypeCache> <item> <key> <int>2201</int> </key> <value> <string>Y</string> </value> </item> <item> <key> <int>2202</int> </key> <value> <string> </string> </value> </item> </DataTypeCache> <IncludePleaseSelect>false</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">2202</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>true</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>26</Order> <Name>NotMetHTypeId</Name> <FriendlyName>H - Contracting delays</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>2200</DataTypeId> <DataType>Type</DataType> <MaxLength>-1</MaxLength> <DataTypeCache> <item> <key> <int>2201</int> </key> <value> <string>Y</string> </value> </item> <item> <key> <int>2202</int> </key> <value> <string> </string> </value> </item> </DataTypeCache> <IncludePleaseSelect>false</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">2202</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>true</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>27</Order> <Name>NotMetITypeId</Name> <FriendlyName>I - Rare diseases</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>2200</DataTypeId> <DataType>Type</DataType> <MaxLength>-1</MaxLength> <DataTypeCache> <item> <key> <int>2201</int> </key> <value> <string>Y</string> </value> </item> <item> <key> <int>2202</int> </key> <value> <string> </string> </value> </item> </DataTypeCache> <IncludePleaseSelect>false</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">2202</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>true</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>28</Order> <Name>NotMetJTypeId</Name> <FriendlyName>J - Other</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>2200</DataTypeId> <DataType>Type</DataType> <MaxLength>-1</MaxLength> <DataTypeCache> <item> <key> <int>2201</int> </key> <value> <string>Y</string> </value> </item> <item> <key> <int>2202</int> </key> <value> <string> </string> </value> </item> </DataTypeCache> <IncludePleaseSelect>false</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">2202</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>false</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>29</Order> <Name>NotMetKTypeId</Name> <FriendlyName>K - Not Used</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>2200</DataTypeId> <DataType>Type</DataType> <MaxLength>-1</MaxLength> <DataTypeCache> <item> <key> <int>2201</int> </key> <value> <string>Y</string> </value> </item> <item> <key> <int>2202</int> </key> <value> <string> </string> </value> </item> </DataTypeCache> <IncludePleaseSelect>false</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">2202</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>false</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>30</Order> <Name>NotMetLTypeId</Name> <FriendlyName>L - Not Used</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>2200</DataTypeId> <DataType>Type</DataType> <MaxLength>-1</MaxLength> <DataTypeCache> <item> <key> <int>2201</int> </key> <value> <string>Y</string> </value> </item> <item> <key> <int>2202</int> </key> <value> <string> </string> </value> </item> </DataTypeCache> <IncludePleaseSelect>false</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">2202</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>false</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>31</Order> <Name>NotMetMTypeId</Name> <FriendlyName>M - Not Used</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>2200</DataTypeId> <DataType>Type</DataType> <MaxLength>-1</MaxLength> <DataTypeCache> <item> <key> <int>2201</int> </key> <value> <string>Y</string> </value> </item> <item> <key> <int>2202</int> </key> <value> <string> </string> </value> </item> </DataTypeCache> <IncludePleaseSelect>false</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">2202</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>false</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>32</Order> <Name>NotMetNTypeId</Name> <FriendlyName>N - Not Used</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>2200</DataTypeId> <DataType>Type</DataType> <MaxLength>-1</MaxLength> <DataTypeCache> <item> <key> <int>2201</int> </key> <value> <string>Y</string> </value> </item> <item> <key> <int>2202</int> </key> <value> <string> </string> </value> </item> </DataTypeCache> <IncludePleaseSelect>false</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">2202</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>false</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>33</Order> <Name>NotMetOTypeId</Name> <FriendlyName>O - Not Used</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>2200</DataTypeId> <DataType>Type</DataType> <MaxLength>-1</MaxLength> <DataTypeCache> <item> <key> <int>2201</int> </key> <value> <string>Y</string> </value> </item> <item> <key> <int>2202</int> </key> <value> <string> </string> </value> </item> </DataTypeCache> <IncludePleaseSelect>false</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">2202</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>String</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>true</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>34</Order> <Name>Comments</Name> <FriendlyName>Comments</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>-1</DataTypeId> <DataType>None</DataType> <MaxLength>-1</MaxLength> <DataTypeCache/> <IncludePleaseSelect>true</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:string"/> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>true</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>35</Order> <Name>ReasonForDelayTypeId</Name> <FriendlyName>Reasons for delay correspond to:</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>2300</DataTypeId> <DataType>Type</DataType> <MaxLength>-1</MaxLength> <DataTypeCache> <item> <key> <int>2301</int> </key> <value> <string>NHS Provider</string> </value> </item> <item> <key> <int>2302</int> </key> <value> <string>Sponsor</string> </value> </item> <item> <key> <int>2303</int> </key> <value> <string>Both</string> </value> </item> <item> <key> <int>2304</int> </key> <value> <string>Neither</string> </value> </item> <item> <key> <int>-1</int> </key> <value> <string>Please Select...</string> </value> </item> </DataTypeCache> <IncludePleaseSelect>true</IncludePleaseSelect> <PleaseSelectIsError>false</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">-1</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings>
Id |  | TrustId |  | SubmissionId |  | MetaSubmissionId |  | Research Ethics Committee Reference Number |  | Name of Trial |  | Date of Receipt of Valid Research Application |  | Date of NHS Permission |  | First Patient Recruited? |  | Date of First Patient Recruited |  | Duration between VRA and NHS Permission |  | Duration between NHS Permission and First Patient |  | Duration between VRA and First Patient |  | Benchmark Met |  | AddedByUserId |  | AmendedByUserId |  | DateAdded |  | DateAmended |  | A - Permissions delayed/denied |  | B - Suspended by sponsor |  | C - Closed by sponsor |  | D - Sponsor Delays |  | E - Staff availability issues |  | F - No patients seen |  | G - No patients consented |  | H - Contracting delays |  | I - Rare diseases |  | J - Other |  | K - Not Used |  | L - Not Used |  | M - Not Used |  | N - Not Used |  | O - Not Used |  | Comments |  | Reasons for delay correspond to:
Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value
blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | 1401 | Yes | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | 1501 | Yes | 294 | Unknown | 294 | Unknown | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | 2201 | Y | 2201 | Y | 2201 | Y | 2201 | Y | 2201 | Y | 2201 | Y | 2201 | Y | 2201 | Y | 2201 | Y | 2201 | Y | 2201 | Y | 2201 | Y | 2201 | Y | 2201 | Y | 2201 | Y | blank£%X_@# | blank£%X_@# | 2301 | NHS Provider
[16 empty] | 1402 | Yes - Date Unavailable | [8 empty] | 1502 | No | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# |  |  |  |  | 2202 |  | 2202 |  | 2202 |  | 2202 |  | 2202 |  | 2202 |  | 2202 |  | 2202 |  | 2202 |  | 2202 |  | 2202 |  | 2202 |  | 2202 |  | 2202 |  | 2202 |  |  |  | 2302 | Sponsor
[16 empty] | 1403 | No | [8 empty] | 1503 | Within 70 Days | [8 empty] | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# |  |  | 2303 | Both
[16 empty] | blank£%X_@# | blank£%X_@# | [8 empty] | -1 | Please Select... | [40 empty] | 2304 | Neither
[26 empty] | blank£%X_@# | blank£%X_@# | [40 empty] | -1 | Please Select...
[68 empty] | blank£%X_@# | blank£%X_@#

## Help
Spreadsheet Help